## Group member 1
To-do list
To be completed by: |  |  |  | Name: Carlos Vega
Deadline: |  |  |  | Date: October 9, 2024
PHW2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Notes:
100% | Planning | 2024-09-30 | 2024-09-30 |  | 1 day | Team meeting where Inderpreet created a group repository to upload work. Disscued the format notebook should follow in regards to markdown and how to utilize chatgpt for help
100% | Preparation | 2024-09-30 | 2024-10-02 |  | 3 days | Read Chapter 8
100% | Chapter 4 exercises 3 and 10 | 2024-10-03 | 2024-10-03 |  | 1 day
100% | Chapter 4 Propositions | 2024-10-03 | 2024-10-04 |  | 2 days | Create 10 propositions based on what we learned in chapter 8. Chapter discussed Data manipulation, which involed operations like, update, delete, bulk, insert e.t.c. My docker still has permission issues when allowing the volume to be accessed by the container. I have create the continer every time i want ot use it.
100% | Chapter 5 exercise 5-1 | 2024-10-05 | 2024-10-05 |  | 1 day
100% | Chapter 5 Propositions | 2024-10-05 | 2024-10-06 |  |  | Create 10 propositions based on what we learned in chapter 8. Used WorldWideImporters database
100% | Paperwork | 2024-09-30 | 2024-10-08 |  | 9 days | Maintained my to-do list up to date with all the work I was doing.
100% | Video Explanation | 2024-10-08 | 2024-10-08 |  | 1 day | Created a video explaining my 10 propositions, edited video to make sure it was within 10 minutes since uncut version was longer than 10 minutes
100% | Submision | 2024-10-09 | 2024-10-09 |  | 1 day | Push all the work to the group repo.