## Group member 1
To-do list
To be completed by: |  |  |  | Name: Carlos Vega
Deadline: |  |  |  | Date: October 9, 2024
PHW2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Notes:
100% | Planning | 2024-09-30 | 2024-09-30 |  | 1 day | Team meeting where Inderpreet created a group repository to upload work. Disscued the format notebook should follow in regards to markdown and how to utilize chatgpt for help
100% | Preparation | 2024-09-30 | 2024-10-02 |  | 3 days | Read Chapter 4 and 5
100% | Chapter 4 exercises 3 and 10 | 2024-10-03 | 2024-10-03 |  | 1 day
100% | Chapter 4 Propositions | 2024-10-03 | 2024-10-04 |  | 2 days | Create 5 propositions based on what we learned in chapter 5. Chapter 5 discussed table expressions, column aliases and other things. WMy docker had permission issues when allowing the volume to be accessed by the container. It took me a long time to figure it out.
100% | Chapter 5 exercise 5-1 | 2024-10-05 | 2024-10-05 |  | 1 day
100% | Chapter 5 Propositions | 2024-10-05 | 2024-10-06 |  |  | Create 5 propositions based on what we learned in chapter 5. Used WideWorldInterpreters database
100% | Paperwork | 2024-09-30 | 2024-10-08 |  | 9 days | Maintained my to-do list up to date with all the work I was doing.
100% | Video Explanation | 2024-10-08 | 2024-10-08 |  | 1 day | Created a video explaining my 10 propositions, edited video to make sure it was within 10 minutes since uncut version was longer than 10 minutes
100% | Submision | 2024-10-09 | 2024-10-09 |  | 1 day | Push all the work to the group repo.